## Sheet1
|  | Initiate |  | Align |  | Implement |  | Validate |  | Launch | Hypercare
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Initiate | Project set up & Planning Meeting | bar: 1
Data Collection | bar: 1 to 2
Align | Requirements Workshops | bar: 3
Requirement Documentation in BRD | bar: 3
Integration File Mappings | bar: 3
BRD review & Approval | bar: 4
Implement | Prepare supplier data for enrollments | bar: 2 to 5
Notify suppliers of upcoming enrollments | bar: 5
Data loading | bar: 5
Enrollments go-live | bar: 1 to 11
System Configuration | bar: 5
Payment file configuration (client) | bar: 5 to 6
Payment file configuration (Corcentric) | bar: 5
Enrollment file configuration (client) | bar: 5 to 6
Enrollment file configuration (Corcentirc) | bar: 5
Create test scripts & test plan | bar: 5 to 6
Validate | Testing Kick off | bar: 7
UAT | bar: 7
Funding testing | bar: 7
UAT fixes | bar: 8
Go-live sign off | bar: 8
Launch | System Live | bar: 1 to 11
Payment file submitted
Hypercare | Monitoring | bar: 10
Transition to Support & CSM | bar: 11